## RFP KANBAN system
Num | Name | Update - Web Link | Remark | Team Concerns | Importance | Riks Level | Assignee | Status | Start date | Due date
Item 1 | 2026 CBRE contract renew | https://www.wrike.com/open.htm?id=4329743021 | RFP Doc/Score Card/Biding |  | High | Red | Jian Xiao | Phase 3 | 12/11/2025 | 06/30/2026
Item 2 | 2026-2027 STS&PDU PPM Contract Renew | https://www.wrike.com/open.htm?id=4390092485 | RFP Doc/Score Card/Biding |  | Medium | Yellow | Allen Geng | Phase 3 | 03/05/2026 | 04/30/2026
Item 3 | DC AV system 2026- 2029 PPM procurement | https://www.wrike.com/open.htm?id=4370120526 | RFP Doc/Score Card/Biding |  | Low | Green | Jian Xiao | Phase 3 | 02/09/2026 | 05/19/2026
Item 4 | GYA & ULA chiller & pump skids and BMS maintenance service purchase application | https://www.wrike.com/open.htm?id=4427989738 | RFP Doc/Score Card/Biding |  | Low | Green | Jian Xiao | Phase 3
Item 5 | Chiller/pumpskid/BMS servie renew | https://www.wrike.com/open.htm?id=1762538040 | SOW/SLA/Impact/Risk review: |  | Low | Green | Jian Xiao | Phase 1 | 04/13/2025 | 06/23/2025
Item 6 | CRAH/MAU/AHU/VRV/Pump maintenance | https://www.wrike.com/open.htm?id=1762538041 | Procurement strategy/Vender list syncing |  | Low | Green | Jian Xiao | Phase 2 | 04/14/2025 | 06/23/2025
Item 7 | Generator service renew | https://www.wrike.com/open.htm?id=1762538043 | Procurement strategy/Vender list syncing |  | Low | Green | Allen Geng | Phase 2 | 04/27/2025 | 07/28/2025
Item 8 | LVSG warranty outage PPM service for phase 2&3 | https://www.wrike.com/open.htm?id=1762538045 | Procurement strategy/Vender list syncing |  | Low | Green | Allen Geng | Phase 2 | 05/13/2025 | 07/20/2025
Item 9 | STS/PDU PPM service renew | https://www.wrike.com/open.htm?id=1762538039 | Procurement strategy/Vender list syncing |  | Low | Green | Allen Geng | Phase 2 | 04/13/2025 | 07/20/2025
Item 10 | Water consultant service renew | https://www.wrike.com/open.htm?id=1762538042 | Procurement strategy/Vender list syncing |  | Low | Green | Jian Xiao | Finished | 04/27/2025 | 11/30/2025
Item 11 | Water treatment contract renew | https://www.wrike.com/open.htm?id=1762538046 | Procurement strategy/Vender list syncing |  | Low | Green | Jian Xiao | Finished | 06/28/2025 | 09/30/2025